MCLEOD LAKE INDIAN BAND LAND CODE – IMPLEMENTATION WORK PLAN

“LC” = McLeod Lake Indian Band Land Code			“IA” = Individual Agreement

“FA” = Framework Agreement on First Nation Management	“FNLMA” = First Nations Land Management Act

| Activity | Deadline | Authority |
| --- | --- | --- |
| Make 14 new reserves subject to Land Code | A.S.A.P. after May 20 | cl. 5.2 LC |
| Make new Bear Lake and Mackenzie reserves subject to Land Code | Whenever designated | cl. 5.3 LC |
| Council establishes register of Laws at main office | A.S.A.P. | cl. 8.3 LC |
| Council and Land Management Committee establishes community process to develop and implement laws set out in cl. 10.1 LC | Within a reasonable time | cl. 10.2 LC |
| Council makes law for procedures at Meetings of Members | Optional | cl. 12.6 LC |
| Council implements system of financial planning and administration | Underway? | cl. 18.2, 19.1 LC |
| Council Resolution to adopt 2003-04 land management budget | June 16, 2003 | cl. 18.3 LC |
| Council presents budget to Members and makes copy available | August 14 – 15, 2003 | cl. 18.5 LC |
| Council prepares 2003-04 financial statement | June, 2004 | cl. 19.2 LC |
| Council maintains bank accounts | Done? | cl. 19.4 LC |
| Council authorizes signing officers | A.S.A.P. | cl. 19.5 LC |
| Council appoints auditor for 2003-04 fiscal year |  | cl. 21.1 LC |
| Council presents auditor’s report to members |  | cl. 21.7 LC |
| Council prepares annual report and tables with Land Management Committee | August 28, 2004 | cl. 22.1 LC |
| Council establishes rules and procedures for listed matters |  | cl. 24.2 LC |
| Council appoints interim Land Management Committee | Done | cl. 25.4 LC |
| Council enacts procedure for Land Management Committee elections |  | cl. 25.8 LC |
| Land Management Committee election | Approx. May 18, 2005 | cl. 25.9 LC |
| Land Management Committee selects chair | Done | cl. 26.1 LC |
| Land Management Committee recommends revenue process, fees, etc. |  | cl. 27.1, 27.2 LC |
| Council establishes Band Land Register | A.S.A.P. | cl. 27.1, 27.2 LC |
| 22. Council establishes standards, criteria, forms for interests and licenses |  | cl. 30.2 LC |
| Council grants interests, licenses and permits with Land Management Committee advice. |  | cl. 32.1, 32.3 LC |
| Council enacts law for granting interests to members |  | cl. 33.1 LC |
| Council allocates lots to members |  | cl. 34.1 LC |
| Council enacts spousal property law | May 21, 2004 | cl. 39.1, 11.1(h) LC; cl. 5.4 FA; cl. 17 FNLMA |
| Lands Management Committee appoints Dispute Resolution Panel |  | cl. 40.3 LC |
| Council to arrange, maintain and pay liability insurance | underway | cl. 44.1, 44.2 LC |
| Develop bilateral or tripartite Environmental Management Agreement (Note: Lands Advisory Board developing template; Band funding to be negotiated with DIA) | May 21, 2004 or prior to enacting environmental laws | Part V, FA; cl. 21 FNLMA |
| Develop Environmental Assessment Process (Canadian Environmental Assessment Act applies in interim; Band funding to be negotiated) | prior to enacting environmental assessment law | Annex F, IA; Part V, FA; cl. 21(3) FNLMA |
| Legal survey descriptions of the McLeod Lake reserves | When available | cl. 6(1)(a) FNLMA |
| Phase 2 Environmental Site Assessment | When negotiated and funded | Annex D, IA |
| Band Council appoints Justice of the Peace, including training and support agreement with Canada and possibly BC; | Optional | cl.19.3 FA |
| Band Council arranges for prosecutorial services | After laws enacted | cl. 19.9 FA |
| Training for Land Management staff | Ongoing |  |
| Official Community Plan and land use planning process, including land value appraisal | Pending |  |
| Other |  |  |

Draft of June 11, 2003